## Test Plan
Section | Description
Introduction | This test plan outlines the strategy and approach for testing the website https://www.saucedemo.com/. The objective is to ensure the functionality, reliability, and performance of the application by conducting various test scenarios, including login attempts, adding products to the cart, and verifying checkout processes.
Test Items | The test items include: - Login functionality - Adding products to the cart - Checkout process - Logout functionality - User interactions with various elements on the page
Test Scope | The scope of the testing includes: In-scope: - Functional testing of login, cart, and checkout functionalities - Validation of error messages - User interactions with the website Out-of-scope: - Performance testing - Security testing - UI/UX design validation
Test Strategy | The testing strategy involves: - Functional Testing: Validate the core functionalities of the website. - Regression Testing: Ensure that new changes do not break existing functionality. - Automated Testing: Utilize Selenium with Java for automating test cases and executing them using TestNG. - Reporting: Generate reports using Extent or Allure for detailed test results. - CI/CD: Integrate test execution with Jenkins and GitHub Actions.
Test Environment | The test environment includes: - Hardware: Standard PC or laptop - Software: Windows OS, latest version of Chrome or Firefox browser - Tools: Selenium WebDriver, TestNG, Jenkins, GitHub, Extent/Allure Reports - Test Data: Valid and invalid usernames and passwords, product details for adding to the cart
Test Schedule | The test schedule is as follows: - Test Planning: 1 week - Test Case Development: 2 weeks - Test Execution: 1 week - Reporting and Analysis: 1 week - Total Duration: 5 weeks
Resources | The testing team includes the following roles and responsibilities: - Test Manager: Oversees the entire testing process - Test Lead: Manages test case development and execution - Automation Engineer: Develops and maintains automated test scripts - Test Analyst: Executes test cases and reports defects - DevOps Engineer: Integrates tests with CI/CD pipeline
Risks and Mitigation | Potential risks and mitigation strategies: - Risk: Delay in test case development Mitigation: Allocate additional resources to speed up the process. - Risk: Test environment issues Mitigation: Set up multiple environments to ensure availability. - Risk: Bugs found in production Mitigation: Perform thorough regression testing before each release.